## Sprint-1
Daily tracker sheet
| Project | Employee TimeSheet |  |  |  | Sprint no | 1
Name | 2022-12-12 | 2022-12-13 | 2022-12-14 | 2022-12-15 | 2022-12-16
Vamsi | Jira Ticket no :MYE-3,MYE-18 Task :Testing,Testcase,Demo Comments:Working on MYE-3 , test case drafting in progress | Jira Ticket no: MYE-3,MYE-18 Started Writing test Cases for (MYE-3) and waiting for review Started Writing Test Cases for(MYE-18) | No update
Nagarjuna | Jira Ticket no :MYE-6,MYE-15 Task :testing,Test cases,Demo Comments: Working on MYE-6 , test case drafting in progress | Jira Ticket no: MYE-6,MYE-15 Started Writing test Cases for (MYE-6) In progress | Jira Ticket no: MYE-6,MYE-15 completed writing test cases sent for review
Ravindra | Jira Ticket no :MYE-9,MYE-12 Task :testing,testcase,Demo Comments:Working on MYE-9 , test case drafting in progress | Jira Ticket no: MYE-9,MYE-12 Started Writing test Cases for (MYE-9) In progress | Jira Ticket no: MYE-9,MYE-12 completed writing test cases sent for review
Umapathi | Jira Ticket no :MYE-16, Task : Dev Comments: Started working on MYE-16 | Jira Ticket no :MYE-16, comments: in progress | Jira Ticket no :MYE-16, comments: in progress
Tharun | Jira Ticket no :MYE-7,MYE-13 Task :Dev Comments: Started working on MYE-7 | Completed MYE-13 user story | Completed MYE-13 user story and working on MYE-7
Sai krishna | Jira Ticket no :MYE-1,MYE-10 Task : DEV Comments: Started working on MYE-1 | Completed MYE-1 user story | Completed MYE-1 user story wokring on MYE-10
praveen | Jira Ticket no :MYE-4 Task :Dev Comments: Started working on MYE-4 | Working in progress (MYE-4) | Working in progress (MYE-4)